## Gantt Chart
MINI ROBOT
Project Name
TASK NAME | START DATE | END DATE | START | DURATION (days)
Phase 1 - Project Planning | 2024-02-19 | 2024-03-17 | 0 | 28
Task 1.1 - Define Project Objective and Scope | 2024-02-19 | 2024-03-17 | 0 | 28
Task 1.2 - Research New and Existing Solutions | 2024-02-19 | 2024-03-17 | 0 | 28
Task 1.3 - Define Project Milestones | 2024-02-19 | 2024-03-17 | 0 | 28
Phase 2 - Design | 2024-02-26 | 2024-03-24 | 7 | 28
Task 2.1 - Conceptualize Robot Design | 2024-02-26 | 2024-03-24 | 7 | 28
Task 2.2 - Develop 3D Models and CAD Drawings | 2024-02-26 | 2024-03-24 | 7 | 28
Task 2.3 - Prototype Components | 2024-02-26 | 2024-03-24 | 7 | 28
Task 2.4 - Conduct Design Reviews | 2024-02-26 | 2024-03-24 | 7 | 28
Phase 3 - Electronic Component Development | 2024-03-18 | 2024-03-31 | 28 | 14
Task 3.1 - Select Actuators | 2024-03-18 | 2024-03-24 | 28 | 7
Task 3.2 - Select Sensors (Proximity Sensors, Camera etc.) | 2024-03-18 | 2024-03-24 | 28 | 7
Task 3.3 - Test Electronic Components | 2024-03-18 | 2024-03-31 | 28 | 14
Phase 4 - Software Development | 2024-03-18 | 2024-04-28 | 28 | 42
Task 4.1 - Develop Control Algorithms | 2024-03-18 | 2024-04-28 | 28 | 42
Task 4.2 - Create User-friendly Interfaces/Modules | 2024-03-18 | 2024-04-28 | 28 | 42
Phase 5 - RPI4 / Camera Layer | 2024-03-31 | 2024-04-28 | 41 | 29
Task 5.1 - Develop 3D Models and CAD Drawings | 2024-03-31 | 2024-04-28 | 41 | 29
Task 5.2 - Electronic Component Development | 2024-03-31 | 2024-04-28 | 41 | 29
Task 5.3 - Integration and Testing | 2024-03-31 | 2024-04-28 | 41 | 29
Phase 6 - Tilt Layer | 2024-03-24 | 2024-04-28 | 34 | 36
Task 6.1 - Develop 3D Models and CAD Drawings | 2024-03-24 | 2024-04-28 | 34 | 36
Task 6.2 - Electronic Component Development | 2024-03-24 | 2024-04-28 | 34 | 36
Task 6.3 - Integration and Testing | 2024-03-24 | 2024-04-28 | 34 | 36
Phase 7 - Deployement and Testing | 2024-04-29 | 2024-06-02 | 70 | 35
Task 7.1 - Demonstartion of the MazeMini Game | 2024-04-29 | 2024-06-02 | 70 | 35
Task 7.2 - Demonstration of the Push Game | 2024-04-29 | 2024-06-02 | 70 | 35
Phase 8 - Documentation | 2024-05-27 | 2024-06-02 | 98 | 7
Task 8.1 - Write Documention for the Modules/Libraries | 2024-05-27 | 2024-06-02 | 98 | 7
Task 8.2 - Write Documentation for the ROS Components | 2024-05-27 | 2024-06-02 | 98 | 7
Phase 9 - Deployement and Testing | 2024-05-06 | 2024-06-02 | 77 | 28
Task 9.1 - Demonstartion of the MazeMini Game | 2024-05-06 | 2024-06-02 | 77 | 28
Task 9.2 - Demonstration of the Push Game | 2024-05-06 | 2024-06-02 | 77 | 28
Task 9.2 - Demonstration of the Push Game | 2024-05-06 | 2024-06-02 | 77 | 28
Phase 10 - ROS Setup and Configuration | 2024-05-20 | 2024-06-02 | 91 | 14
Task 10.1 - Install ROS framework and required packages | 2024-03-10 | 2024-03-24 | 20 | 15
Task 10.2 - Configure ROS workspace and environment variables | 2024-03-24 | 2024-04-24 | 34 | 32
Task 10.3 - Plan the Communication Structure and Setup the Protocols | 2024-03-31 | 2024-05-24 | 41 | 55
Formulas:
START = DATEDIF(C6,[START DATE],"D")
DURATION (days) = DATEDIF([START DATE],[END DATE],"D")+1
MILESTONE 1:
00/00/00
Brief Description